**UPTON NP – TIMELINE 2021** DRAFT Jan 2021

**JAN** Preparations for Final Consultation

**FEB-MAR** Final Consultation (Reg 14)

**MAR-APR** Prepare Consultation Statement, Revised Draft Plan (Submission Version) and Basic Conditions Statement

**MAY** Submission Version of NeighbourhoodPlan signed off by Parish Council

**MAY** Submit Plan to CWAC (Reg 15)

**JUN-JULY** CWaCC publicise Plan (Reg 16) and appoint Examiner

**JULY** CWaCC submit Plan to Examination (Reg 17)

**SEPT** Examiner’s report published (Reg 18)

 CWaCC issues decision statement & publishes information

**OCT-NOV** Preparations for referendum (CWaCC)

**NOV Referendum**

Plan “made”

 Plan publicised by CWaCC (Reg 20)

**DEC-** Process for ongoing monitoring of NP set up by Parish Council