**YOUR UPTON 2030: TIMELINE TO MEET OCT 2019 REFERENDUM**

**2018**

**April - Oct:** Policy subgroups draft Policies and gather Evidence

**Nov:** Parish Council sign off draft policies

Author/s prepare pre-submission draft Plan

**Dec-Mid Jan:** Consult on pre-submission draft (Reg 14)

**2019**

**Mid Jan-Feb:** Revise Plan and gain Parish Council sign-off

**Early March:** Submit Plan to CWAC (Reg 15)

**Mar-April:** CWAC publicise Plan (Reg 16) and appoint Examiner

**May:** CWAC submit Plan to Examination (Reg 17)

**July:** Examiner’s report published (Reg 18)

 CWAC issues decision statement & publishes information

**Aug-Sept:** Preparations for referendum

**Oct: Referendum**

Plan “made”

 Plan publicised (Reg 20)