**UPTON NP – REVISED TIMELINE 2020-2021**

**2020**

**AUG** Postal Consultation with Dale residents in private housing

Apply to Locality for grant for Plan Health Check

**SEPT** Parish Council sign off Consultation Draft Plan

CWAC consultation including SEA and Habitats Regulations

Consultation with MoD, COCH and Zoo

**OCT** Full Sustainability Appraisal if required (CWAC to advise)

Plan Health Check

**NOV-DEC** Revised Consultation Draft Plan signed off by Parish Council

Preparations made for Final Consultation with residents

**2021**

**JAN** Final Consultation with Residents (Reg 14)

**FEB** Final Draft Plan signed off by Parish Council

**MAR** Submit Plan to CWAC (Reg 15)

**MAR-APR** CWAC publicise Plan (Reg 16) and appoint Examiner

**MAY** CWAC submit Plan to Examination (Reg 17)

**JULY** Examiner’s report published (Reg 18)

CWAC issues decision statement & publishes information

**AUG-SEPT** Preparations for referendum

**OCT Referendum**

Plan “made”

Plan publicised (Reg 20)